## Timeline
Week# | Justin | Marcus | Zach | David | Discussion | Assignment | Milestones | SDLC Stages | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19
1
2 |  |  |  |  | Plans and Specifications | Project Plan |  | Stage 1: Planning and Requirement Analysis
3 | Github Setup | Desktop GUI | Database | Desktop GUI | User's Guide and Test Plan | Test Plan | Establish Requirements | Stage 2: Defining Requirements
4 | ^ | ^ | ^ | UML Diagram | Design | Project Design | Put Design On Paper | Stage 3: Designing the Product Architecture
5 | ^ | ^ | ^ | ^ | Phase 1 | Phase 1 Source | Finish Initial Feature Set | Stage 4: Building or Developing the Product Stage 5: Testing the Product
6 | Web UI | Report Generator | Authenticator | Income Tracker | Phase 2 | Phase 2 Source | Include / Test Add'l Feature | ^
7 | ^ | ^ | ^ | ^ | Phase 3 | Phase 3 Source | Include / Test Add'l Feature | ^
8 | [5 empty] | Project Report

## Task Ack
Week# | Justin |  | Marcus |  | Zach |  | David
| Task and Acknowledgement |  | .. |  | .. |  | ..
2 | Task: Access Teams & Github | X | Task: Access Teams & Github | X | Task: Access Teams & Github | X | Task: Access Teams & Github | X
3 | Task: Tools (Github) | X | Task: Desktop GUI research | X | Task: Database research | X | Task: Desktop GUI research | X
| Task: Asdf |  | Task: Asdf |  | Task: Asdf |  | Task: Asdf
4 | Task: Asdf |  | Task: Asdf |  | Task: Asdf |  | Task: UML Diagram
5
6 | Task: Web UI |  | Task: Report Generator |  | Task: Authenticator |  | Task: Income Tracker
7
8

## Roles
Developer | Component | Role | Responsibilites | Column5
David | Desktop GUI
Zach | Database
Marcus | Desktop GUI
Justin | Web UI | Group Leader | Coordinate team responsibilities
Overall Team Responsibilities:
1 | Complete each relevant stage of the SDLC
2 | Gather information and research
3 | Design plans for the application itself, testing, individual components, etc.
4
5